CONSTRUCTION MANAGER AT RISK AGREEMENT

This Construction Manager at Risk Agreement ("Agreement") is entered into effective ${start_date} ("Effective Date"), by and between:

${owner_company_name}, a North Carolina local government, whose mailing address is:

${owner_address_line1}
${owner_address_line2}
${owner_city_state_zip}

("Owner")

and

${counterparty_company_name}, whose principal office is located at:

${counterparty_address_line1}
${counterparty_address_line2}
${counterparty_city_state_zip}

("Construction Manager" or "CMAR").

The Owner and the Construction Manager may be referred to individually as a "Party" and collectively as the "Parties."

# RECITALS

WHEREAS, the Owner intends to construct, renovate, improve, or otherwise complete the public project identified herein;

WHEREAS, the Owner has determined that the Construction Manager at Risk project delivery method is in the best interests of the public pursuant to N.C. Gen. Stat. §143-128.1A and applicable North Carolina law;

WHEREAS, the Construction Manager represents that it possesses the qualifications, personnel, equipment, experience, financial capability, and licenses necessary to perform the services required by this Agreement;

WHEREAS, the Owner selected the Construction Manager through a qualifications-based selection process or other procurement method authorized by North Carolina law;

WHEREAS, the Parties desire to establish the terms under which the Construction Manager will provide preconstruction services, construction phase services, and, when authorized, construct the Project pursuant to a Guaranteed Maximum Price ("GMP");

NOW, THEREFORE, in consideration of the mutual covenants contained herein, the Parties agree as follows.

# ARTICLE 1

# PROJECT

## 1.1 Project

The Construction Manager shall provide professional construction management services for the following Project:

Project Name

${name}

Project Description

${description}

The Project shall be administered on behalf of the Owner by:

Department:

${department_name}

Department Code:

${department_code}

## 1.2 Contract Information

Contract Number:

${contract_number}

Contract Type:

${contract_type_name}

Procurement Method:

${procurement_method}

Procurement Reference Number:

${bid_rfp_number}

Purchase Order Number:

${po_number}

Account Number:

${account_number}

## 1.3 Contract Value

If a Guaranteed Maximum Price has been established, the current authorized Contract Value shall be:

${total_contract_value_dollars}

(${total_contract_value_words})

Unless modified by written Change Order or GMP Amendment executed by both Parties.

## 1.4 Contract Documents

The Contract Documents consist of:

- This Agreement

- All executed Amendments

- Guaranteed Maximum Price Amendments

- Change Orders

- Drawings

- Specifications

- Addenda

- Written Modifications

- Supplemental Conditions

- General Conditions

- All Exhibits attached to this Agreement

- The documents listed in:

${exhibit_list}

The Contract Documents are intended to be complementary. If conflicts exist, the more stringent requirement shall control unless otherwise directed by the Owner.

# ARTICLE 2

# DEFINITIONS

For purposes of this Agreement, the following definitions shall apply.

## 2.1 Agreement

Agreement means this Construction Manager at Risk Agreement together with all properly executed amendments and incorporated exhibits.

## 2.2 Architect

The licensed architect or engineer retained by the Owner to prepare the Project design documents.

## 2.3 Change Order

A written modification executed by the Owner and Construction Manager changing the Contract Time, Guaranteed Maximum Price, Scope of Work, or other Contract requirement.

## 2.4 Construction Documents

The drawings, specifications, technical requirements, and other design documents prepared for construction.

## 2.5 Construction Manager

The entity identified as:

${counterparty_company_name}

which has entered into this Agreement with the Owner.

## 2.6 Cost of the Work

Those costs necessarily incurred in properly performing the Work and specifically allowed under this Agreement and any GMP Amendment.

Costs not expressly allowed shall be considered included within the Construction Manager's Fee.

## 2.7 Final Completion

The point at which:

- all Work has been completed;

- all punch list items have been completed unless otherwise accepted by Owner;

- all closeout documents have been delivered;

- warranties have commenced;

- Owner has accepted the Project.

## 2.8 Guaranteed Maximum Price (GMP)

The maximum amount payable by the Owner for completion of the Work, as established by written GMP Amendment.

The GMP may only be modified by executed Change Order or written GMP Amendment.

## 2.9 Owner

The municipal corporation identified as:

${owner_company_name}

## 2.10 Project

The work described in Article 1 together with all associated labor, services, equipment, materials, permits, supervision, administration, and incidentals necessary to achieve Final Completion.

## 2.11 Subcontractor

Any individual or entity retained by the Construction Manager to perform any portion of the Work.

## 2.12 Work

All labor, supervision, equipment, professional services, materials, supplies, coordination, administration, construction, commissioning, and closeout necessary to complete the Project in accordance with the Contract Documents.

# ARTICLE 3

# TERM

## 3.1 Effective Date

This Agreement becomes effective on:

${start_date}

## 3.2 Contract Duration

Unless earlier terminated in accordance with this Agreement, this Agreement shall remain in effect until:

${end_date}

or Final Completion of all obligations, whichever occurs later.

## 3.3 Renewals

Automatic Renewal:

${auto_renew}

Renewal Term:

${renewal_term_months} months

No renewal shall be effective unless authorized by applicable North Carolina law and appropriated by the governing board.

## 3.4 Time is of the Essence

Time is of the essence in the performance of this Agreement.

The Construction Manager shall prosecute the Work diligently and continuously to achieve all milestone dates established by the Contract Documents.

Failure to maintain progress constitutes grounds for corrective action, withholding of payment, or termination as provided herein.

# ARTICLE 4

# GENERAL OBLIGATIONS OF THE CONSTRUCTION MANAGER

The Construction Manager shall perform all services with the degree of care, skill, diligence, and professional judgment ordinarily exercised by experienced construction managers performing comparable public projects in North Carolina.

The Construction Manager acknowledges that it is being retained because of its specialized expertise and shall serve as the Owner's professional construction advisor throughout the Project.

The Construction Manager shall:

- act in good faith toward the Owner;

- protect the Owner's interests;

- coordinate the Project efficiently;

- continuously monitor cost, schedule, constructability, and quality;

- promptly notify the Owner of any matter that could materially affect cost, schedule, quality, or safety;

- cooperate fully with the Owner, Architect, consultants, and regulatory agencies;

- maintain qualified personnel throughout the Project;

- comply with all applicable federal, state, and local laws, ordinances, regulations, and permit requirements;

- maintain complete and accurate project records; and

- avoid conflicts of interest in the performance of its services.

The Construction Manager shall not proceed with work beyond the scope authorized by the Owner without prior written approval.

End of Part 1

The next section will begin Article 5 – Preconstruction Services, which is one of the most important portions of a CMAR agreement. It will include detailed provisions governing estimating, value engineering, constructability reviews, scheduling, bidding packages, long-lead procurement, BIM coordination, risk identification, and preparation of the Guaranteed Maximum Price proposal.

ARTICLE 5

PRECONSTRUCTION SERVICES

5.1 General

Beginning upon the Effective Date of this Agreement, the Construction Manager shall provide comprehensive preconstruction services to assist the Owner and the Architect in developing the Project in a manner that promotes quality, constructability, schedule certainty, budget control, and long-term operational value.

The Construction Manager shall act as the Owner's professional construction advisor throughout the design phase and shall continuously evaluate the Project for opportunities to improve quality, reduce risk, minimize cost, accelerate construction, and enhance maintainability.

The Construction Manager acknowledges that preconstruction services constitute professional services and shall exercise the degree of care and skill ordinarily exercised by experienced construction managers performing similar public projects within North Carolina.

5.2 Scope of Preconstruction Services

The Construction Manager shall provide, at a minimum, the following services:

a. review all design documents;

b. participate in design meetings;

c. review the proposed scope of work for completeness;

d. advise regarding construction sequencing;

e. recommend construction phasing;

f. identify long-lead procurement items;

g. recommend alternative construction methods;

h. review site logistics;

i. evaluate utility conflicts;

j. identify permitting issues;

k. coordinate with public utility providers;

l. evaluate temporary facilities;

m. review access and traffic control;

n. assist in maintaining the Project budget;

o. assist in maintaining the Project schedule;

p. prepare cost estimates;

q. identify risks affecting cost or schedule;

r. recommend value engineering opportunities;

s. prepare procurement packages for subcontractors; and

t. perform such additional preconstruction services as reasonably requested by the Owner.

5.3 Design Reviews

At each stage of design, the Construction Manager shall review the drawings and specifications for:

- constructability;

- completeness;

- coordination between disciplines;

- code compliance issues apparent from the documents;

- material availability;

- labor availability;

- long-term maintenance considerations;

- life-cycle costs;

- sequencing conflicts;

- safety concerns;

- schedule impacts;

- procurement risks; and

- cost impacts.

The Construction Manager shall promptly submit written comments to the Owner and Architect identifying recommended revisions.

Failure to identify an issue during design review shall not relieve the Construction Manager of responsibility for performing the Work in accordance with the Contract Documents.

5.4 Constructability Review

The Construction Manager shall conduct ongoing constructability reviews throughout the design process.

Constructability reviews shall include, at a minimum:

- conflicting details;

- missing information;

- impractical construction methods;

- excessive complexity;

- coordination between architectural, structural, civil, mechanical, plumbing, electrical, and technology systems;

- staging requirements;

- crane access;

- temporary utilities;

- site access;

- weather impacts;

- commissioning requirements;

- material substitutions;

- maintenance accessibility; and

- anticipated contractor coordination issues.

Written constructability review reports shall be submitted at each design milestone unless otherwise directed by the Owner.

5.5 Value Engineering

The Construction Manager shall continuously evaluate opportunities to improve value.

Value engineering recommendations shall:

- maintain or improve Project quality;

- preserve intended function;

- reduce cost where practical;

- reduce long-term operating expenses;

- improve maintainability;

- shorten construction duration where appropriate;

- improve energy efficiency where feasible; and

- reduce lifecycle costs.

The Construction Manager shall prepare written value engineering recommendations identifying:

- existing design;

- proposed alternative;

- estimated cost savings;

- schedule impacts;

- operational impacts;

- maintenance implications; and

- recommendation.

The Owner retains sole discretion regarding acceptance of any value engineering recommendation.

5.6 Cost Estimating

The Construction Manager shall prepare detailed cost estimates throughout design.

Unless otherwise directed by the Owner, estimates shall be prepared at approximately:

- Schematic Design;

- Design Development;

- Fifty Percent Construction Documents;

- Ninety Percent Construction Documents;

- One Hundred Percent Construction Documents; and

- immediately prior to submission of the Guaranteed Maximum Price.

Each estimate shall include:

- labor;

- materials;

- equipment;

- subcontractor costs;

- allowances;

- contingencies;

- escalation;

- general conditions;

- Construction Manager Fee;

- permits;

- testing;

- temporary facilities;

- insurance;

- bonds;

- anticipated taxes;

- construction contingency; and

- Owner contingency, if applicable.

Each estimate shall identify assumptions made in preparing the estimate.

5.7 Budget Monitoring

The Construction Manager shall continuously monitor Project costs.

If the Construction Manager determines that the Project is likely to exceed the Owner's approved budget, the Construction Manager shall immediately notify the Owner in writing.

The notice shall include:

- estimated overrun;

- reason for overrun;

- recommended corrective actions;

- schedule impacts; and

- estimated savings associated with each recommendation.

5.8 Schedule Development

The Construction Manager shall prepare and maintain a detailed Project schedule.

The schedule shall identify each of the following: design milestones; permitting activities; utility coordination; procurement activities; subcontract bidding; long-lead procurement; Owner decisions; construction phases; inspections; commissioning; substantial completion; final completion.

The schedule shall be updated at least monthly during preconstruction.

5.9 Long-Lead Procurement

The Construction Manager shall identify equipment and materials having extended procurement periods.

The Construction Manager shall recommend procurement strategies to minimize schedule delays.

No long-lead procurement shall occur without written authorization from the Owner.

Ownership of long-lead materials purchased prior to establishment of the GMP shall be governed by written agreement.

  - Subcontract Packaging

The Construction Manager shall recommend logical bid packages designed to the extent possible and practical, that does each of the following: maximize competition; encourage participation by qualified subcontractors; improve scheduling; reduce overall Project cost; facilitate minority and women-owned business participation; and minimize trade conflicts.

Bid packages shall be subject to Owner approval.

5.11 Permitting Assistance

The Construction Manager shall assist the Owner and Architect in identifying permits, approvals, and regulatory requirements applicable to the Project.

The Construction Manager shall maintain a permit tracking log identifying: required permits; responsible party; anticipated submission dates; approval dates; expiration dates; and conditions affecting construction.

  - xisting Conditions

The Construction Manager shall review available information regarding: surveys;  geotechnical reports; utility information; environmental reports; hazardous materials; easements; rights-of-way; adjacent property conditions; and  existing infrastructure.

The Construction Manager shall promptly notify the Owner of any condition that may materially affect Project cost, schedule, or constructability.

5.13 Risk Identification

The Construction Manager shall continuously evaluate Project risks.

Risk assessments shall include: labor shortages; material availability; inflation; escalation; weather impacts; permitting delays; utility conflicts; unknown site conditions; supply chain disruptions; regulatory changes; subcontractor availability; and market conditions.

The Construction Manager shall recommend mitigation strategies for identified risks.

5.14 Guaranteed Maximum Price Proposal

Upon completion of the design phase or when directed by the Owner, the Construction Manager shall prepare a detailed Guaranteed Maximum Price Proposal.

The proposal shall include, at a minimum:

- Cost of the Work;

- Construction Manager Fee;

- General Conditions;

- Construction contingency;

- Allowances;

- Assumptions and clarifications;

- List of exclusions;

- Detailed schedule;

- Cash flow projection;

- Schedule of values;

- Proposed subcontract awards;

- Supporting cost documentation;

- Unit prices, if applicable;

- Bonds;

- Insurance costs; and

- Any additional information reasonably requested by the Owner.

The GMP Proposal shall remain open for acceptance by the Owner for not less than sixty (60) days unless otherwise agreed.

The Owner may accept, reject, negotiate, or request revisions to the GMP Proposal. No GMP shall become effective unless approved in writing by the Owner through a formally executed GMP Amendment.

5.15 Standard of Care

The Construction Manager shall perform all preconstruction services in accordance with the professional standard of care applicable to experienced construction managers providing comparable services for public projects in North Carolina.

The Construction Manager shall not be liable for design errors or omissions made by the Architect or Engineer; however, the Construction Manager shall promptly notify the Owner and Architect of any errors, omissions, conflicts, or deficiencies that are known or should reasonably have been identified through the exercise of professional diligence during the performance of its preconstruction services.

5.16 No Guarantee of Design

Nothing in this Agreement shall be construed to require the Construction Manager to warrant the adequacy of the design prepared by the Owner's Architect or Engineer. The Construction Manager's responsibility is to exercise professional skill and care in reviewing the design documents and advising the Owner regarding constructability, cost, schedule, and coordination.

ARTICLE 6

GUARANTEED MAXIMUM PRICE (GMP)

6.1 Establishment of the Guaranteed Maximum Price

The Construction Manager shall prepare and submit a Guaranteed Maximum Price Proposal ("GMP Proposal") when directed by the Owner.

No Guaranteed Maximum Price shall become effective unless approved in writing by the Owner and incorporated into this Agreement through a written GMP Amendment executed by both Parties.

Until execution of a GMP Amendment, the Construction Manager shall perform only those services expressly authorized by the Owner.

6.2 GMP Amendment

Each GMP Amendment shall include, at a minimum:

a. the Guaranteed Maximum Price;

b. the Cost of the Work;

c. the Construction Manager's Fee;

d. General Conditions costs;

e. Allowances;

f. Construction Contingency;

g. Owner Contingency, if any;

h. Project Schedule;

i. list of accepted alternates;

j. list of exclusions;

k. assumptions relied upon in establishing the GMP;

l. schedule of values;

m. milestone dates;

n. liquidated damages, if applicable;

o. unit prices, if applicable; and

p. any other documents required by the Owner.

6.3 Guaranteed Maximum Price

The Guaranteed Maximum Price shall constitute the maximum amount payable by the Owner for completion of the Work unless modified by Change Order or executed GMP Amendment.

The Construction Manager assumes the risk of all costs in excess of the Guaranteed Maximum Price except as expressly provided herein.

6.4 Open Book Pricing

The Guaranteed Maximum Price shall be developed using an open-book methodology.

The Construction Manager shall provide complete supporting documentation sufficient to permit the Owner to independently verify all proposed costs.

Supporting documentation shall include, as applicable: subcontractor bids; supplier quotations; labor burden calculations; equipment rates; insurance costs; bond costs; General Conditions; fee calculations; contingency calculations; escalation assumptions; allowances; takeoffs; quantity summaries; and any additional documentation reasonably requested by the Owner.

Failure to provide requested documentation may constitute grounds for rejection of the GMP Proposal.

6.5 Components of the GMP

The Guaranteed Maximum Price shall consist only of:

- Cost of the Work;

- Construction Manager Fee;

- approved General Conditions;

- approved Allowances;

- approved Construction Contingency;

- applicable taxes;

- insurance;

- bonds; and

- other costs expressly approved by the Owner.

No other compensation shall be due unless authorized by written Change Order.

6.6 Construction Manager Fee

The Construction Manager's Fee shall be specifically identified within the GMP.

Unless otherwise provided in the GMP Amendment, the Fee shall include compensation for: corporate overhead; executive supervision; home office expenses; profit; administrative support; estimating; accounting; legal expenses; ordinary business expenses; office equipment; software; communications; travel; and all costs not expressly identified as Cost of the Work.

The Fee shall not be increased except through executed Change Order.

6.7 Cost of the Work

Only those costs expressly identified as allowable within this Agreement and the GMP Amendment shall constitute Cost of the Work.

Costs not specifically identified as allowable shall be deemed included within the Construction Manager's Fee.

The burden of demonstrating allowability rests upon the Construction Manager.

6.8 Allowances

The GMP may include Allowances for portions of the Work that cannot reasonably be determined at the time the GMP is established.

Each Allowance shall identify:

- description;

- amount;

- intended use;

- assumptions;

- procurement method.

Unused portions of Allowances shall be credited to the Owner.

Expenditures exceeding an Allowance shall require written Owner approval.

6.9 Construction Contingency

The GMP may include a Construction Contingency solely for unforeseen costs reasonably anticipated during construction.

Construction Contingency shall not be used for: Construction Manager negligence; estimating errors; coordination failures; subcontractor default; warranty work; correction of defective work; costs otherwise included within the Fee; costs or expenses, including that of any subcontractor, which should have been anticipated or known to the Construction Manager prior to providing the GMP to the Owner.

Use of Construction Contingency shall require prior written approval by the Owner unless otherwise provided in the GMP Amendment.

The Construction Manager shall maintain a Contingency Log identifying each expenditure and the remaining balance.

6.10 Owner Contingency

The Owner may establish a separate Owner Contingency.

Owner Contingency shall remain under the exclusive control of the Owner.

No portion of Owner Contingency shall become payable to the Construction Manager without written authorization from the Owner.

6.11 Savings

If the final Cost of the Work is less than the Guaranteed Maximum Price, the resulting savings shall belong exclusively to the Owner unless a written shared savings provision is expressly included within the applicable GMP Amendment.

No implied right to savings sharing shall exist.

6.12 Shared Savings (Optional)

If expressly authorized within a GMP Amendment, the Parties may share savings below the Guaranteed Maximum Price.

The GMP Amendment shall establish: calculation methodology; exclusions; reconciliation procedures; maximum shared amount; timing of payment.

Absent an executed shared savings provision, all savings belong solely to the Owner.

6.13 Market Escalation

Except as expressly provided in an executed GMP Amendment, the Construction Manager assumes the risk of material price escalation, labor escalation, tariffs, market fluctuations, and supply chain increases occurring after establishment of the Guaranteed Maximum Price.

Requests for additional compensation based solely upon general market conditions shall not constitute grounds for adjustment of the GMP.

6.14 Procurement Before GMP

The Owner may authorize procurement of long-lead materials prior to establishment of the Guaranteed Maximum Price.

Such authorization shall not obligate the Owner to approve the proposed GMP.

Ownership of materials procured before execution of the GMP shall be governed by written authorization issued by the Owner.

6.15 Subcontractor Bidding

The Construction Manager shall competitively solicit subcontractor proposals in accordance with applicable North Carolina law and the Owner's procurement requirements.

Unless otherwise approved by the Owner:

- multiple qualified bids shall be obtained for each trade package where practicable;

- bid tabulations shall be maintained;

- all subcontractor selections shall be documented;

- the Owner may participate in bid opening and evaluation.

The Construction Manager shall recommend subcontract awards; however, final approval shall remain with the Owner to the extent permitted by law.

6.16 Self-Performed Work

The Construction Manager shall not perform construction work with its own forces unless:

a. specifically disclosed during procurement;

b. competitively priced or otherwise authorized by law;

c. approved in writing by the Owner; and

d. consistent with applicable North Carolina statutes.

The Construction Manager shall maintain documentation demonstrating that self-performed work is in the Owner's best interest.

6.17 Schedule of Values

Prior to commencement of construction, the Construction Manager shall submit a detailed Schedule of Values allocating the Guaranteed Maximum Price among all portions of the Work.

The Owner shall approve the Schedule of Values before the first Application for Payment.

6.18 GMP Reconciliation

Upon Final Completion, the Construction Manager shall provide a complete reconciliation of the Guaranteed Maximum Price.

The reconciliation shall include: original GMP; approved Change Orders; Allowance adjustments; Contingency usage; Cost of the Work; Fee; unused Allowances; unused Contingency; Owner credits; shared savings calculations, if applicable.

The Owner shall have the right to audit all supporting records.

6.19 Audit Rights

The Owner, its auditors, or other authorized representatives shall have the right to inspect and audit all books, records, invoices, payroll records, subcontract agreements, purchase orders, quotations, accounting records, and other documents supporting the Guaranteed Maximum Price or any payment request.

Such records shall be retained for not less than five (5) years after Final Completion, or for any longer period required by applicable law.

If an audit reveals an overpayment of more than one percent (1%) of the audited amount, the Construction Manager shall reimburse the Owner for the overpayment together with the reasonable costs of the audit.

6.20 Payments Pending Audit

The Owner's approval of a payment application shall not constitute acceptance of the accuracy of the underlying cost documentation.

The Owner may subsequently audit any payment and recover any amount determined to have been improperly paid.

No final payment shall waive the Owner's right to recover overpayments discovered after completion of an audit.

6.21 Contract Information

The current approved Guaranteed Maximum Price, if established, is reflected in the Contract Information maintained by the Owner.

Current Contract Value:

${total_contract_value_dollars}

(${total_contract_value_words})

Purchase Order:

${po_number}

Account Number:

${account_number}

Nothing contained in these administrative fields shall modify the legal obligations established by this Article unless incorporated into an executed GMP Amendment.

# ARTICLE 7

# CONSTRUCTION PHASE SERVICES

## 7.1 Commencement of Construction

The Construction Manager shall commence construction only after:

a. execution of a Guaranteed Maximum Price Amendment, unless otherwise authorized by the Owner;

b. issuance of a Notice to Proceed;

c. receipt of all required permits necessary to commence the applicable phase of the Work;

d. delivery of required bonds and insurance certificates; and

e. satisfaction of all conditions precedent established by the Contract Documents.

## 7.2 General Responsibility

The Construction Manager shall furnish all labor, supervision, materials, equipment, temporary facilities, transportation, tools, services, administration, and incidentals necessary to complete the Work in accordance with the Contract Documents.

The Construction Manager shall be solely responsible for construction means, methods, techniques, sequences, procedures, temporary works, and coordination of the Work unless the Contract Documents expressly assign such responsibility to another party.

## 7.3 Standard of Performance

The Construction Manager shall perform the Work:

- in a good and workmanlike manner;

- in accordance with industry standards applicable to public construction projects;

- in compliance with all applicable laws, codes, regulations, and permits;

- using qualified and properly supervised personnel;

- with due regard for public safety and the Owner's operations; and

- in accordance with the Contract Documents.

The Construction Manager shall promptly correct any Work that does not conform to these requirements.

## 7.4 Project Superintendent

The Construction Manager shall designate a competent Project Superintendent who shall be present at the Project site whenever Work is being performed unless otherwise approved by the Owner.

The Superintendent shall have authority to:

- receive instructions from the Owner;

- coordinate subcontractors;

- direct construction activities;

- maintain project records;

- implement safety procedures; and

- resolve day-to-day construction issues.

The Owner may require replacement of the Superintendent for reasonable cause. The Construction Manager shall promptly provide a qualified replacement.

## 7.5 Project Manager

The Construction Manager shall assign a Project Manager responsible for overall administration of the Project.

The Project Manager shall remain actively involved throughout construction and shall attend meetings requested by the Owner.

Replacement of the Project Manager shall require prior notice to the Owner.

## 7.6 Coordination of the Work

The Construction Manager shall coordinate all portions of the Work, including the activities of subcontractors, suppliers, consultants, testing laboratories, inspectors, utility providers, and others performing services related to the Project.

The Construction Manager shall schedule the Work to minimize conflicts, delays, disruption to Owner operations, and unnecessary interference with adjacent property owners.

## 7.7 Progress Schedule

The Construction Manager shall maintain a detailed Critical Path Method (CPM) schedule or other Owner-approved scheduling system.

The schedule shall identify:

- major activities;

- procurement;

- submittals;

- shop drawings;

- fabrication;

- delivery dates;

- inspections;

- testing;

- commissioning;

- substantial completion;

- final completion; and

- Owner occupancy milestones.

The schedule shall be updated at least monthly and more frequently if requested by the Owner.

## 7.8 Recovery Schedule

If the Construction Manager falls behind the approved schedule, the Owner may require submission of a written Recovery Schedule.

The Recovery Schedule shall identify actions necessary to recover lost time without additional cost to the Owner unless otherwise approved by written Change Order.

Acceptance of a Recovery Schedule shall not waive the Owner's right to assess damages or pursue other remedies.

## 7.9 Progress Meetings

The Construction Manager shall conduct regular progress meetings at intervals established by the Owner.

Attendees may include:

- Owner representatives;

- Architect;

- engineers;

- major subcontractors;

- utility representatives;

- testing agencies;

- commissioning personnel; and

- others designated by the Owner.

The Construction Manager shall prepare and distribute meeting minutes within five (5) business days after each meeting.

## 7.10 Daily Reports

The Construction Manager shall maintain daily project reports documenting:

- weather conditions;

- workforce;

- subcontractors present;

- equipment on site;

- deliveries;

- inspections;

- visitors;

- accidents;

- delays;

- work completed;

- photographs when appropriate; and

- unusual events affecting the Project.

Daily reports shall become part of the Project record and shall be available to the Owner upon request.

## 7.11 Quality Control

The Construction Manager shall establish and maintain a comprehensive Quality Control Program.

The program shall include:

- inspection procedures;

- testing coordination;

- document control;

- correction of deficiencies;

- verification of completed work;

- punch list management; and

- coordination with commissioning activities.

The Construction Manager shall inspect all Work before requesting inspection by the Owner or Architect.

## 7.12 Defective Work

The Construction Manager shall promptly correct Work that is:

- defective;

- damaged;

- non-conforming;

- improperly installed;

- incomplete; or

- otherwise inconsistent with the Contract Documents.

Correction shall occur promptly after notice from the Owner or upon discovery by the Construction Manager.

Failure of the Owner to reject defective Work immediately shall not constitute acceptance.

## 7.13 Temporary Facilities

The Construction Manager shall provide and maintain all temporary facilities necessary for performance of the Work, including:

- temporary utilities;

- field offices;

- sanitation facilities;

- fencing;

- barricades;

- erosion control measures;

- temporary lighting;

- temporary access roads;

- storage facilities; and

- site security.

Unless otherwise provided in the Contract Documents, temporary facilities shall be removed before Final Completion.

## 7.14 Site Security

The Construction Manager shall secure the Project site and protect materials, equipment, and completed Work against theft, vandalism, weather, and unauthorized access.

The Owner shall not be responsible for loss or damage to construction equipment, tools, temporary facilities, or materials stored on site prior to acceptance of the Work, except to the extent caused by the Owner's negligence or willful misconduct.

## 7.15 Protection of Existing Property

The Construction Manager shall protect existing buildings, utilities, landscaping, roadways, sidewalks, and other improvements affected by the Work.

Damage caused by the Construction Manager or its subcontractors shall be repaired or replaced at no additional cost to the Owner.

## 7.16 Public Safety

The Construction Manager shall conduct construction activities in a manner that protects:

- the public;

- employees;

- visitors;

- adjacent property owners;

- utility infrastructure; and

- Owner personnel.

The Construction Manager shall implement appropriate traffic control, pedestrian protection, signage, barricades, and other safety measures required by law or reasonably necessary under the circumstances.

## 7.17 Environmental Protection

The Construction Manager shall comply with all applicable environmental laws and permit requirements.

The Construction Manager shall implement measures necessary to control:

- erosion;

- sedimentation;

- dust;

- stormwater pollution;

- noise;

- debris;

- hazardous materials;

- spills; and

- waste disposal.

The Construction Manager shall immediately report any environmental incident that could materially affect the Project or public safety.

## 7.18 Owner Access

The Owner, Architect, engineers, inspectors, testing agencies, funding agencies, regulatory authorities, and other authorized representatives shall have reasonable access to the Project site at all times.

The Construction Manager shall cooperate with inspections and shall provide reasonable assistance necessary to facilitate review of the Work.

## 7.19 Coordination with Owner Operations

Where construction occurs on an occupied site or adjacent to active municipal operations, the Construction Manager shall coordinate its activities to minimize disruption to:

- governmental services;

- emergency response;

- utility operations;

- schools;

- parks;

- public streets;

- public facilities; and

- neighboring properties.

The Construction Manager shall comply with operational restrictions established by the Owner.

## 7.20 Communications

The Construction Manager shall designate a primary point of contact for communications with the Owner.

Instructions affecting cost, schedule, or scope shall be documented in writing.

The Construction Manager shall promptly notify the Owner of any event that may materially affect:

- Project cost;

- schedule;

- quality;

- safety;

- permitting;

- regulatory compliance; or

- public operations.

## 7.21 Photographic Documentation

The Construction Manager shall maintain photographic documentation of construction progress at intervals reasonably acceptable to the Owner.

Photographs shall include:

- existing conditions;

- concealed work prior to covering;

- significant milestones;

- completed systems;

- punch list items; and

- final completed Work.

Digital photographs shall become part of the Project record and shall be delivered to the Owner at Project closeout.

## 7.22 Project Records

Throughout construction, the Construction Manager shall maintain complete and accurate Project records, including:

- correspondence;

- meeting minutes;

- schedules;

- daily reports;

- submittals;

- requests for information (RFIs);

- change documentation;

- testing reports;

- inspection reports;

- permits;

- payment records;

- warranty information; and

- other documents reasonably required by the Owner.

Such records shall be organized in a manner that permits efficient review and shall remain available for inspection by the Owner throughout the Project.

ARTICLE 8

SUBCONTRACTORS AND PROCUREMENT OF THE WORK

8.1 General Responsibility

The Construction Manager shall furnish all labor, materials, equipment, and services necessary to complete the Work either through its own approved forces or through properly qualified subcontractors and suppliers.

The Construction Manager shall remain fully responsible for the acts, omissions, defaults, negligence, and performance of every subcontractor, supplier, lower-tier subcontractor, consultant, and person employed directly or indirectly by the Construction Manager.

No subcontract shall relieve the Construction Manager of any obligation under this Agreement.

8.2 Competitive Procurement

Subcontracts shall be procured in accordance with applicable North Carolina law, the Contract Documents, and any procurement procedures established by the Owner.

The Construction Manager shall maximize competition while obtaining qualified subcontractors capable of performing the Work.

The Construction Manager shall not divide work into smaller packages for the purpose of avoiding applicable procurement requirements.

8.3 Bid Packages

Prior to soliciting subcontractor proposals, the Construction Manager shall prepare proposed bid packages for Owner review.

Each package shall clearly identify:

- Scope of Work;

- technical requirements;

- drawings and specifications;

- schedule requirements;

- insurance requirements;

- bonding requirements, where applicable;

- alternates;

- allowances;

- unit prices, if applicable; and

- subcontract terms.

The Owner may require reasonable revisions to proposed bid packages prior to advertisement.

8.4 Solicitation of Bids

The Construction Manager shall publicly or privately solicit subcontractor proposals as permitted by applicable law and the Contract Documents.

Reasonable efforts shall be made to notify qualified subcontractors capable of performing each portion of the Work.

The Construction Manager shall maintain documentation identifying:

- firms solicited;

- firms responding;

- bid dates;

- bid amounts;

- scope clarifications;

- bid irregularities; and

- reasons for rejecting proposals.

8.5 Bid Evaluation

Subcontractor selection shall be based upon the best interests of the Project, considering factors including:

- qualifications;

- experience;

- financial capability;

- safety history;

- proposed schedule;

- past performance;

- responsiveness;

- references;

- ability to meet Project requirements;

- price; and

- compliance with procurement requirements.

Selection shall not be based solely upon the lowest proposed price unless required by applicable law or the Contract Documents.

8.6 Owner Participation

The Owner may:

- observe bid openings;

- review bid tabulations;

- request copies of proposals;

- participate in evaluation meetings;

- request interviews with proposed subcontractors; and

- review supporting documentation used in making subcontract award recommendations.

The Owner's participation shall not relieve the Construction Manager of responsibility for selecting competent subcontractors or managing their performance.

8.7 Recommendation of Awards

The Construction Manager shall recommend proposed subcontract awards to the Owner.

Each recommendation shall include: proposed subcontractor; trade package; proposed subcontract amount; comparison of bids received; explanation of any recommendation other than the lowest responsive proposal; confirmation of qualifications; and any other information reasonably requested by the Owner.

Where Owner approval is required by law or the Contract Documents, no subcontract shall be executed until such approval has been obtained.

8.8 Self-Performed Work

The Construction Manager shall not perform construction work with its own forces unless:

- the intent to self-perform was disclosed during procurement;

- the Owner has approved such work in writing;

- pricing has been established through competitive means or otherwise determined acceptable by the Owner; and

- self-performance complies with applicable North Carolina law.

The Construction Manager shall maintain complete documentation supporting all self-performed work.

8.9 Minority and Women-Owned Business Participation

The Construction Manager shall make good-faith efforts to encourage participation by historically underutilized businesses, minority-owned businesses, women-owned businesses, and other firms identified by applicable North Carolina law or Owner policy.

The Construction Manager shall maintain documentation of outreach efforts, solicitations, meetings, and participation.

Upon request, the Construction Manager shall provide reports identifying subcontractor participation by trade and business classification.

Nothing contained herein shall require the selection of an unqualified subcontractor or the use of quotas inconsistent with applicable law.

8.10 Subcontract Requirements

Every subcontract shall require the subcontractor to comply with all applicable provisions of the Contract Documents.

Without limitation, each subcontract shall include provisions concerning: safety;  insurance; warranties; indemnification; record retention; audit rights; payment; compliance with laws; correction of defective work; termination; dispute resolution, where applicable; and assignment of warranties to the Owner.

The Construction Manager shall be responsible for ensuring that subcontract agreements are consistent with this Agreement.

8.11 Subcontractor Default

If a subcontractor defaults or fails to perform satisfactorily, the Construction Manager shall promptly take all actions reasonably necessary to protect the Project.

Such actions may include: supplemental staffing; corrective action plans; replacement of the subcontractor; enforcement of subcontract remedies; use of performance security; or other reasonable measures.

Costs resulting from subcontractor default shall be borne by the Construction Manager unless otherwise expressly provided by Change Order.

8.12 Supplier Selection

The Construction Manager shall purchase materials and equipment from responsible suppliers capable of providing products meeting the requirements of the Contract Documents.

The Construction Manager shall verify compatibility, availability, lead times, warranties, and manufacturer requirements prior to procurement.

8.13 Long-Lead Procurement

Where early procurement has been authorized, the Construction Manager shall maintain a procurement log identifying:

- item description;

- supplier;

- purchase order date;

- anticipated delivery;

- actual delivery;

- storage location;

- warranty status; and

- installation schedule.

The Construction Manager shall protect Owner-owned materials until incorporated into the Work.

8.14 Assignment of Subcontracts

No subcontract shall be assigned without the written consent of the Construction Manager.

Assignment affecting the Owner's interests shall additionally require written Owner approval.

8.15 Payment to Subcontractors

The Construction Manager shall promptly pay subcontractors in accordance with applicable law and the terms of the applicable subcontract.

The Owner reserves the right to require evidence that subcontractors have been paid as a condition of future progress payments.

Upon request, the Construction Manager shall provide: lien waivers;  payment affidavits; supplier releases;  proof of payment; or other documentation reasonably requested by the Owner.

8.16 Subcontractor Meetings

The Construction Manager shall conduct coordination meetings with subcontractors as necessary to maintain Project progress.

Meeting minutes shall be maintained as part of the Project record.

8.17 Owner's Right to Reject

The Owner may reasonably object to the use of a proposed subcontractor based upon:

- demonstrated lack of qualifications;

- documented poor performance on comparable projects;

- financial instability;

- licensing deficiencies;

- safety concerns;

- conflicts of interest;

- inability to meet Project requirements; or

- other reasonable grounds affecting successful Project completion.

If the Owner rejects a proposed subcontractor, the Construction Manager shall promptly recommend an alternative qualified firm.

8.18 No Contractual Relationship

Nothing contained in this Agreement shall create any contractual relationship between the Owner and any subcontractor or supplier.

The Construction Manager shall remain solely responsible for administration of all subcontracts.

No subcontractor shall have any direct claim against the Owner except to the extent expressly provided by applicable law.

8.19 Procurement Records

The Construction Manager shall maintain complete procurement records for all trade packages, including:

- advertisements;

- solicitations;

- bid tabulations;

- evaluations;

- award recommendations;

- executed subcontracts;

- amendments;

- payment records; and

- correspondence.

Such records shall remain subject to the Owner's audit rights under this Agreement.

ARTICLE 9

BONDS, INSURANCE, AND RISK MANAGEMENT

9.1 Performance and Payment Bonds

Before commencing construction, and as a condition precedent to the issuance of a Notice to Proceed, the Construction Manager shall furnish separate Performance and Payment Bonds, each in the full amount of the Guaranteed Maximum Price, or such other amount required by North Carolina law. Each bond shall be executed by a surety company authorized to transact business within the State of North Carolina and acceptable to the Owner.

The Performance Bond shall guarantee the faithful performance of all obligations under the Contract Documents. The Payment Bond shall guarantee payment to all persons furnishing labor, materials, equipment, or services for the Project in accordance with Chapter 44A of the North Carolina General Statutes and other applicable law.

The Construction Manager shall maintain the bonds in full force and effect until Final Completion of the Work and satisfaction of all warranty obligations required by the Contract Documents. If the surety becomes insolvent or otherwise unacceptable to the Owner, the Construction Manager shall promptly furnish replacement security acceptable to the Owner.

9.2 Insurance Requirements

The Construction Manager shall procure and maintain, at its own expense, insurance policies issued by insurers licensed or otherwise authorized to conduct business in North Carolina and having financial strength reasonably acceptable to the Owner. Such insurance shall remain continuously in effect throughout the performance of the Work and during any period in which warranty or corrective obligations remain outstanding, where applicable.

Coverage shall be sufficient to protect the Construction Manager, the Owner, and the public against claims arising from the performance of the Work. The minimum insurance limits and required coverages shall be set forth in Exhibit B or such other insurance schedule as may be adopted by the Owner and incorporated into this Agreement.

If the Owner has designated that a Certificate of Insurance is required, the Construction Manager shall comply with that requirement as reflected in the Contract Information:

Certificate of Insurance Required: ${minimum_insurance_coi}

The Construction Manager represents that its current Certificate of Insurance expires on ${counterparty_coi_exp_date_formatted}, unless subsequently renewed and replaced with updated evidence of coverage.

9.3 Certificates of Insurance

Prior to commencing the Work, the Construction Manager shall furnish certificates of insurance demonstrating compliance with this Agreement. The certificates shall identify the Project, the Owner, the applicable policy numbers, policy limits, effective dates, and expiration dates.

Renewal certificates shall be provided not less than ten (10) days before expiration of any required policy. Failure to maintain required insurance shall constitute a material breach of this Agreement.

The Owner's acceptance of certificates of insurance shall not waive any requirement of this Agreement nor limit the Construction Manager's responsibility for maintaining adequate insurance coverage.

9.4 Additional Insured Status

Except for Workers' Compensation and Professional Liability insurance, the Construction Manager shall cause the Owner, its elected officials, officers, employees, agents, and volunteers to be named as Additional Insureds under the Construction Manager's Commercial General Liability, Automobile Liability, Umbrella Liability, and other applicable liability policies, to the fullest extent permitted by law.

Such coverage shall apply on a primary and non-contributory basis with respect to insurance maintained by the Owner.

9.5 Builders Risk Insurance

Unless otherwise provided in the Contract Documents, the Owner shall determine whether Builders Risk insurance will be furnished by the Owner or by the Construction Manager.

If Builders Risk insurance is to be provided by the Construction Manager, such insurance shall insure against direct physical loss or damage to the Work while under construction and shall remain in effect until Substantial Completion or such later date as required by the Contract Documents.

The Construction Manager shall be responsible for all deductibles associated with losses arising from its negligence or the negligence of its subcontractors unless otherwise agreed in writing.

9.6 Workers' Compensation

The Construction Manager shall maintain Workers' Compensation insurance meeting all requirements of the North Carolina Workers' Compensation Act together with Employers' Liability insurance in amounts reasonably acceptable to the Owner.

The Construction Manager shall require every subcontractor performing Work on the Project to maintain comparable coverage.

9.7 Automobile Liability

The Construction Manager shall maintain Automobile Liability insurance covering all owned, non-owned, leased, and hired vehicles used in connection with the Project.

Such coverage shall apply to bodily injury, property damage, and contractual liability arising from operation of motor vehicles associated with the Work.

9.8 Professional Liability

To the extent the Construction Manager provides professional services, including construction management consulting, estimating, scheduling, constructability review, Building Information Modeling (BIM) coordination, or other professional services requiring the exercise of professional judgment, the Construction Manager shall maintain Professional Liability insurance in amounts reasonably acceptable to the Owner.

Such coverage shall remain in effect for not less than three (3) years following Final Completion unless a longer period is required by the Contract Documents.

9.9 Waiver of Subrogation

To the extent permitted by law, the Construction Manager and the Owner waive all rights against one another for damages covered by property insurance maintained in accordance with this Agreement, except where such waiver would impair the rights of a governmental entity or conflict with applicable North Carolina law.

This waiver shall not apply to losses resulting from fraud, willful misconduct, criminal acts, or obligations not covered by applicable insurance.

9.10 Safety Responsibilities

The Construction Manager acknowledges that it has sole responsibility for initiating, maintaining, supervising, and enforcing all safety precautions and programs in connection with the Work.

The Construction Manager shall comply with all applicable federal, state, and local occupational safety laws, including regulations promulgated by the Occupational Safety and Health Administration and the North Carolina Department of Labor.

The Construction Manager shall immediately notify the Owner of any fatality, serious injury, regulatory citation, environmental incident, or other occurrence that materially affects Project safety or performance.

Nothing contained in this Agreement shall be construed as transferring responsibility for construction site safety to the Owner, Architect, or any consultant retained by the Owner.

9.11 Hazardous Materials

If the Construction Manager discovers hazardous materials, unknown contamination, or environmental conditions differing materially from those disclosed by the Owner, the Construction Manager shall immediately suspend the affected Work, secure the area, notify the Owner in writing, and comply with all applicable regulatory requirements.

The Construction Manager shall not disturb suspected hazardous materials except as authorized by applicable law and the Owner.

Unless the hazardous condition results from the acts or omissions of the Construction Manager or its subcontractors, appropriate adjustments to the Contract Sum or Contract Time shall be addressed through the Change Order process.

9.12 Property Protection

The Construction Manager shall take all reasonable precautions to protect existing buildings, utilities, roadways, sidewalks, landscaping, adjacent property, and completed portions of the Work from damage resulting from construction activities.

Any damage caused by the Construction Manager or its subcontractors shall be repaired or replaced promptly at no additional cost to the Owner.

9.13 Indemnification

To the fullest extent permitted by North Carolina law, the Construction Manager shall indemnify and hold harmless the Owner and its officers, officials, employees, and agents from and against claims, damages, losses, liabilities, fines, penalties, judgments, and reasonable attorneys' fees arising out of or resulting from the negligent acts or omissions, recklessness, or willful misconduct of the Construction Manager, its employees, subcontractors, suppliers, or any person for whom the Construction Manager is legally responsible.

This obligation shall not be construed to require the Construction Manager to indemnify the Owner against the Owner's own negligence except to the extent permitted by applicable law. Nothing contained herein shall be interpreted as a waiver of the Owner's governmental immunity or sovereign immunity.

9.14 Limitation on Owner Liability

The Owner shall not be responsible for loss of or damage to construction equipment, temporary facilities, tools, scaffolding, machinery, or materials owned or rented by the Construction Manager except to the extent directly caused by the negligent acts or omissions of the Owner.

9.15 Risk Manager Review

Execution of this Agreement may be subject to review by the Owner's Risk Manager. The administrative record shall reflect the date of such approval as:

${risk_manager_approval_date}

The absence of an administrative approval date within the Contract Information shall not invalidate this Agreement unless such approval is expressly required by applicable law or the Owner's internal policies.

oval is expressly required by applicable law or the Owner's internal policies.

ARTICLE 10

PAYMENT, RETAINAGE, AND ACCOUNTING

10.1 Contract Compensation

As full compensation for the performance of the Work, the Owner shall pay the Construction Manager the amounts properly due under this Agreement and any executed Guaranteed Maximum Price Amendment, subject to the terms and conditions of the Contract Documents. Except as expressly provided herein, the Construction Manager shall have no claim for additional compensation unless authorized by a written Change Order or other written amendment executed by the Parties.

The current Contract Value reflected in the Owner's records is:

Contract Value: ${total_contract_value_dollars}

Amount in Words: ${total_contract_value_words}

Nothing contained in the Contract Information shall modify the Guaranteed Maximum Price except through a properly executed amendment.

10.2 Applications for Payment

The Construction Manager shall submit Applications for Payment no more frequently than once each calendar month unless otherwise approved by the Owner.

Each Application for Payment shall accurately reflect the value of Work completed through the date of the application and shall include sufficient supporting documentation to permit verification by the Owner.

At a minimum, each application shall include the approved Schedule of Values, an updated construction schedule, a summary of previous payments, current work completed, stored materials for which payment is requested, approved Change Orders, pending Change Order requests, contingency usage, allowance balances, subcontractor payment information, and such additional documentation as the Owner may reasonably require.

Submission of an Application for Payment constitutes the Construction Manager's representation that the Work for which payment is requested has been performed in accordance with the Contract Documents.

10.3 Review of Payment Applications

The Owner and the Architect, if applicable, shall review each Application for Payment for conformity with the Contract Documents.

The Owner may request additional information, supporting documentation, clarification, or correction before approving payment.

Approval of an Application for Payment shall not constitute acceptance of defective Work, approval of unauthorized changes, or waiver of any rights under this Agreement.

10.4 Conditions to Payment

The Owner shall not be obligated to make any payment until the Construction Manager has complied with all applicable requirements of this Agreement.

The Owner may require, as a condition of payment, submission of certified payroll information where applicable, updated schedules, lien waivers, affidavits of payment to subcontractors and suppliers, evidence of insurance, updated contingency reports, certified cost records, and any other documentation reasonably necessary to verify the amount requested.

Failure to provide requested documentation shall constitute sufficient grounds for withholding payment until the deficiency has been corrected.

10.5 Stored Materials

The Owner may, in its discretion, approve payment for properly stored materials not yet incorporated into the Work, provided the Construction Manager demonstrates that title to the materials will vest in the Owner upon payment, the materials are properly identified for the Project, adequately insured, protected from damage, and available for inspection.

Payment for stored materials shall not constitute acceptance of such materials nor relieve the Construction Manager of responsibility for loss, damage, or proper incorporation into the Work.

10.6 Retainage

The Owner may withhold retainage from progress payments to the extent permitted by North Carolina law and the Contract Documents.

Retainage shall serve as security for the faithful performance of the Work and shall not be construed as a limitation upon any other rights or remedies available to the Owner.

The Owner may reduce or release retainage when authorized by law and when, in the Owner's judgment, the interests of the Project are adequately protected.

10.7 Payments to Subcontractors

Within the time required by applicable law and the terms of each subcontract, the Construction Manager shall promptly pay subcontractors and suppliers amounts properly due for Work included in progress payments received from the Owner.

Upon request, the Construction Manager shall provide satisfactory evidence that subcontractors and suppliers have been paid.

If the Owner has reasonable grounds to believe that subcontractors or suppliers have not been timely paid, the Owner may require additional documentation before approving future Applications for Payment.

10.8 Withholding of Payment

Notwithstanding any other provision of this Agreement, the Owner may withhold all or any portion of an Application for Payment to protect the Owner from loss resulting from circumstances including, but not limited to, defective Work, incomplete Work, failure to correct deficiencies, disputed claims, failure to pay subcontractors or suppliers, damage to the Work or other property, failure to maintain required insurance or bonds, material schedule delays, inaccurate payment applications, failure to provide required documentation, or any material breach of this Agreement.

The Owner shall notify the Construction Manager of the basis for withholding payment and shall release withheld amounts when the underlying condition has been satisfactorily resolved.

10.9 Audit of Costs

Because this Agreement is based upon open-book accounting principles, the Construction Manager shall maintain complete and accurate financial records supporting every amount charged to the Project.

The Owner shall have the right, upon reasonable notice, to examine, inspect, copy, and audit all records relating to the Project, including payroll records, invoices, purchase orders, subcontract agreements, accounting records, equipment logs, time records, correspondence, electronic data, and other documentation reasonably necessary to verify Project costs.

The Construction Manager shall cooperate fully with any audit conducted by or on behalf of the Owner.

10.10 Disallowed Costs

Any cost determined by the Owner to be unsupported, unreasonable, duplicative, unauthorized, or otherwise inconsistent with the Contract Documents shall be disallowed.

If payment has previously been made for a disallowed cost, the Construction Manager shall promptly reimburse the Owner or authorize the Owner to deduct such amount from future payments.

The Owner's determination shall be subject to the dispute resolution procedures contained in this Agreement.

10.11 Final Application for Payment

Following Final Completion, the Construction Manager shall submit a Final Application for Payment together with all documents required for Project closeout.

The Final Application shall include a final accounting of the Guaranteed Maximum Price, all approved Change Orders, contingency usage, allowance reconciliations, outstanding credits, and any remaining balance due.

The Construction Manager shall certify that all obligations arising out of the Project have been satisfied except those specifically identified in writing.

10.12 Conditions Precedent to Final Payment

The Owner shall not be obligated to make Final Payment until the Construction Manager has delivered all closeout documentation required by the Contract Documents.

Such documentation shall include, as applicable, final lien waivers, affidavits of payment, consent of surety, warranties, operating manuals, maintenance manuals, as-built drawings, record documents, training documentation, commissioning reports, certificates of occupancy, final inspection approvals, and all other documents required by this Agreement.

10.13 Final Payment Not Acceptance

Neither Final Payment nor occupancy of the Project shall constitute acceptance of defective, incomplete, or nonconforming Work.

Final Payment shall not waive any claim arising from latent defects, fraud, warranty obligations, inaccurate accounting, defective materials, improper workmanship, or other matters that could not reasonably have been discovered prior to Final Payment.

10.14 Appropriation of Funds

The obligations of the Owner under this Agreement are subject to the availability and lawful appropriation of funds.

Nothing contained herein shall obligate the governing board to appropriate funds in any future fiscal year.

In the event sufficient funds are not appropriated for continued performance of this Agreement, the Owner may terminate this Agreement without penalty upon written notice to the Construction Manager. The Construction Manager shall be entitled only to payment for Work properly performed through the effective date of termination.

10.15 Payment Terms

Unless otherwise provided in the Contract Documents, approved invoices shall be paid in accordance with the following payment terms maintained in the Contract Information:

Payment Terms: ${payment_terms_name}

${payment_terms_description}

Purchase Order Number: ${po_number}

Account Number: ${account_number}

Administrative payment information maintained by the Owner shall not alter the legal rights and obligations established by this Agreement.

ARTICLE 11

CHANGES IN THE WORK

11.1 Owner's Right to Order Changes

The Owner may, at any time during the performance of the Work, order additions, deletions, revisions, modifications, or other changes within the general scope of the Project. Such changes shall not invalidate this Agreement.

The Construction Manager shall not perform any change affecting the Contract Sum, Guaranteed Maximum Price, or Contract Time without written authorization from the Owner, except where immediate action is reasonably necessary to protect life, public safety, or property. In such event, the Construction Manager shall notify the Owner as soon as practicable and shall document the circumstances giving rise to the emergency.

11.2 Written Authorization Required

No oral instruction, field discussion, meeting conversation, shop drawing review, inspection comment, or other informal communication shall authorize a change in the Work or entitle the Construction Manager to additional compensation or additional time.

Only a written Change Order or other written directive executed by an authorized representative of the Owner may modify the Contract Sum, the Guaranteed Maximum Price, or the Contract Time.

The Construction Manager proceeds with any unauthorized work at its own risk.

11.3 Proposed Changes

Whenever the Construction Manager believes that circumstances require a modification to the Work, it shall promptly submit a written request describing the proposed change.

The request shall include a detailed explanation of the reason for the change, the portion of the Work affected, the anticipated impact upon cost, the anticipated impact upon the Project Schedule, any effect upon previously completed work, and any additional information reasonably requested by the Owner.

Failure to provide timely notice may constitute a waiver of any claim arising from the proposed change to the extent the Owner is materially prejudiced by the delay.

11.4 Pricing of Changes

The Construction Manager shall provide complete pricing documentation supporting every requested adjustment to the Contract Sum.

Pricing shall be based upon one or more of the following methods, as determined by the Owner:

(1) mutually agreed lump sum pricing;

(2) unit prices established by the Contract Documents;

(3) negotiated cost supported by complete documentation; or

(4) force account, if specifically authorized by the Owner.

All pricing shall be developed using the same open-book accounting principles applicable to the Guaranteed Maximum Price.

The Owner may require copies of quotations, supplier pricing, subcontractor proposals, labor calculations, equipment rates, payroll records, invoices, and any other documentation necessary to verify the proposed adjustment.

11.5 Time Extensions

The Construction Manager shall not be entitled to an extension of the Contract Time unless the change directly affects the critical path of the approved Project Schedule.

Requests for additional time shall be submitted promptly after the Construction Manager becomes aware of the circumstances giving rise to the request and shall include a detailed schedule analysis demonstrating the effect upon Project completion.

The Construction Manager shall take all reasonable steps to mitigate delays before requesting an extension of time.

11.6 Concealed or Unknown Conditions

If the Construction Manager encounters concealed or unknown physical conditions that materially differ from those ordinarily encountered or from those reasonably indicated by the Contract Documents, the Construction Manager shall immediately stop the affected portion of the Work and provide written notice to the Owner.

The Owner may investigate the condition and determine whether an adjustment to the Contract Sum or Contract Time is appropriate.

Failure to provide prompt written notice before disturbing the condition may prejudice the Construction Manager's entitlement to additional compensation or time.

11.7 Regulatory Changes

If, after execution of this Agreement, a change in applicable federal, state, or local law directly requires modification of the Work, the Parties shall negotiate an equitable adjustment to the Contract Sum or Contract Time, provided the Construction Manager promptly notifies the Owner after becoming aware of the regulatory change.

11.8 Minor Changes

The Owner or Architect may authorize minor changes in the Work that do not affect the Contract Sum, Guaranteed Maximum Price, quality, intended function, or Contract Time.

Such minor changes may be documented through written field directives, supplemental instructions, or other written administrative documents approved by the Owner.

11.9 Emergencies

In the event of an emergency threatening life, public safety, or significant property damage, the Construction Manager shall act immediately to protect persons and property.

The Construction Manager shall notify the Owner as soon as reasonably practicable and shall maintain complete documentation of all emergency actions taken.

Nothing contained herein shall authorize the Construction Manager to permanently modify the Project without subsequent written approval by the Owner.

11.10 Construction Manager Duty to Proceed

Pending resolution of any dispute concerning a proposed change, the Construction Manager shall continue diligent performance of the Work unless otherwise directed in writing by the Owner.

The existence of a dispute regarding compensation or Contract Time shall not justify suspension or abandonment of the Work.

11.11 Effect of Executed Change

Once executed, a Change Order shall constitute full and final compensation for the work described therein, including all direct costs, indirect costs, overhead, profit, schedule impacts, acceleration, disruption, inefficiency, and cumulative impacts arising from the change, unless the Change Order expressly reserves a specific matter for future determination.

11.12 Changes Within the Guaranteed Maximum Price

Where a proposed modification may be accomplished using available Construction Contingency or unused Allowances, the Owner may direct that the work proceed without increasing the Guaranteed Maximum Price.

Nothing contained herein shall require the Owner to utilize contingency funds rather than adjusting the Guaranteed Maximum Price through a formal Change Order.

11.13 Audit Rights

All records supporting any requested adjustment to the Contract Sum or Contract Time shall remain subject to the Owner's audit rights under this Agreement.

The Construction Manager shall retain such documentation for not less than five (5) years following Final Completion or for any longer period required by law.

11.14 No Implied Waiver

The Owner's review of pricing, participation in negotiations, issuance of Requests for Information, field observations, inspections, payment of progress estimates, or failure to immediately object to construction activities shall not constitute approval of any change or waiver of the Owner's rights under this Agreement.

No waiver shall be effective unless made in writing by an authorized representative of the Owner.

ARTICLE 12

PROJECT SCHEDULE, DELAYS, AND LIQUIDATED DAMAGES

12.1 Time of Performance

Time is of the essence in the performance of this Agreement. The Construction Manager shall prosecute the Work diligently and continuously from the date of the Notice to Proceed until Final Completion and shall achieve all milestone dates established by the Contract Documents.

The Construction Manager shall organize, supervise, coordinate, and sequence the Work so as to avoid unnecessary delay and shall provide sufficient labor, equipment, supervision, and resources to maintain progress in accordance with the approved Project Schedule.

12.2 Project Schedule

Before commencing construction, the Construction Manager shall prepare a detailed Project Schedule for review and approval by the Owner. The schedule shall identify all major activities necessary for completion of the Project, including procurement, permitting, submittals, shop drawings, fabrication, inspections, utility coordination, commissioning, Substantial Completion, and Final Completion.

The approved Project Schedule shall become the baseline schedule for administration of the Project. The Construction Manager shall update the schedule at least monthly, or more frequently if requested by the Owner or required by the Contract Documents.

Approval of the Project Schedule by the Owner shall not relieve the Construction Manager of responsibility for completing the Work within the Contract Time.

12.3 Progress of the Work

The Construction Manager shall continuously monitor the progress of the Work and shall promptly take all reasonable measures necessary to maintain the approved Project Schedule.

If the Construction Manager becomes aware of any condition that may delay completion of the Project, it shall immediately notify the Owner in writing. Such notice shall describe the cause of the anticipated delay, the anticipated duration of the delay, the portions of the Work affected, and the corrective measures proposed by the Construction Manager.

The Construction Manager shall not delay providing notice while awaiting complete information regarding the extent of the delay.

12.4 Recovery Schedule

If the Owner determines that the Work is not progressing in accordance with the approved Project Schedule, the Owner may require the Construction Manager to prepare and implement a Recovery Schedule.

The Recovery Schedule shall identify the specific measures the Construction Manager will undertake to regain lost time and shall demonstrate how the Construction Manager intends to achieve the required completion date.

Unless otherwise approved through a Change Order, the Construction Manager shall implement the Recovery Schedule without additional compensation.

12.5 Excusable Delays

The Construction Manager shall be entitled to an extension of the Contract Time only for delays that are beyond its reasonable control and that directly affect the critical path of the Project Schedule.

Excusable delays may include unusually severe weather, acts of God, acts of war, terrorism, widespread labor disruptions not caused by the Construction Manager, governmental actions not resulting from the Construction Manager's conduct, epidemics or pandemics having a direct effect upon Project performance, concealed conditions qualifying under this Agreement, or other extraordinary events that could not reasonably have been anticipated.

The Construction Manager shall not be entitled to additional compensation for an excusable delay unless such compensation is expressly authorized by this Agreement or approved by written Change Order.

12.6 Non-Excusable Delays

The Construction Manager shall not be entitled to an extension of the Contract Time or additional compensation for delays resulting from its own acts or omissions, the acts or omissions of its subcontractors or suppliers, equipment failures, labor shortages that could reasonably have been anticipated, inadequate staffing, improper scheduling, estimating errors, procurement failures, financial difficulties, or other causes within the Construction Manager's reasonable control.

12.7 Concurrent Delays

If a delay results from concurrent causes, one of which is attributable to the Construction Manager and one of which is excusable, any adjustment to the Contract Time shall be determined based upon the extent to which the excusable event independently affected the critical path of the Project.

The Construction Manager shall have the burden of demonstrating entitlement to any extension of time.

12.8 Notice of Delay

A request for adjustment of the Contract Time shall be submitted in writing within fourteen (14) calendar days after the Construction Manager first becomes aware, or reasonably should have become aware, of the event giving rise to the request.

The request shall include a detailed description of the event, the anticipated impact on the Project Schedule, supporting documentation, and a schedule analysis demonstrating the effect upon the critical path.

Failure to provide timely notice may result in denial of the request to the extent the Owner is materially prejudiced by the delay.

12.9 Schedule Analysis

Whenever requested by the Owner, the Construction Manager shall provide a schedule analysis demonstrating the impact of any claimed delay upon the approved Project Schedule.

The schedule analysis shall identify the affected activities, the duration of the delay, the critical path, mitigation efforts undertaken, and the revised anticipated completion date.

The Owner may require additional supporting documentation before approving any adjustment of the Contract Time.

12.10 Acceleration

The Owner may direct the Construction Manager to accelerate the Work when necessary to protect the public interest or achieve Project objectives.

If the acceleration is not the result of the Construction Manager's failure to perform, the Parties shall negotiate an equitable adjustment to the Contract Sum and, if appropriate, the Contract Time.

If acceleration is required because of delays attributable to the Construction Manager, no additional compensation shall be due.

12.11 Liquidated Damages

If the Contract Documents establish liquidated damages for failure to achieve Substantial Completion or Final Completion within the Contract Time, the Parties acknowledge that actual damages resulting from delayed completion would be difficult to ascertain and that the agreed liquidated damages constitute a reasonable estimate of the Owner's anticipated damages and are not intended as a penalty.

Liquidated damages, if applicable, shall be established in the applicable GMP Amendment or other Contract Document. If no liquidated damages amount is specified, no liquidated damages shall apply.

Assessment of liquidated damages shall not preclude the Owner from exercising any other remedy available under this Agreement except to the extent such remedy would result in an impermissible double recovery.

12.12 Early Completion

The Construction Manager shall not be entitled to additional compensation for completing the Work ahead of schedule unless the Parties have entered into a written incentive agreement expressly providing for such compensation.

12.13 Suspension of the Work

The Owner may suspend all or any portion of the Work whenever the Owner determines that suspension is necessary for the protection of the Project, public safety, funding, regulatory compliance, or the public interest.

Upon receipt of a written suspension directive, the Construction Manager shall promptly secure the Work, protect completed construction, minimize additional costs, and comply with the Owner's instructions.

If a suspension is caused by the Construction Manager's default or failure to perform, no adjustment to the Contract Sum or Contract Time shall be allowed.

If the suspension is not attributable to the Construction Manager and materially affects Project performance, the Parties may negotiate an equitable adjustment through the Change Order process.

12.14 Failure to Maintain Progress

If the Construction Manager persistently fails to maintain adequate progress, fails to provide sufficient labor or equipment, or otherwise jeopardizes timely completion of the Project, the Owner may require the Construction Manager to increase staffing, work additional shifts, provide additional equipment, revise sequencing, or implement other reasonable corrective measures.

Unless otherwise approved in writing, the cost of such corrective measures shall be borne by the Construction Manager.

12.15 No Waiver

The Owner's failure to object to delays, acceptance of updated schedules, approval of progress payments, participation in progress meetings, or continued occupancy or use of the Project shall not constitute a waiver of the Owner's right to enforce the Contract Time or seek remedies for delayed performance.

ARTICLE 13

SUBSTANTIAL COMPLETION, FINAL COMPLETION, WARRANTIES, AND CORRECTION OF THE WORK

13.1 Substantial Completion

Substantial Completion shall occur when the Work, or an identified portion thereof, is sufficiently complete in accordance with the Contract Documents so that the Owner may occupy or utilize the Project for its intended purpose without material interference, notwithstanding the existence of minor incomplete or corrective work that does not materially impair the safe or intended use of the Project.

The Construction Manager shall provide written notice to the Owner when it believes the Project has achieved Substantial Completion and shall request an inspection by the Owner and the Architect, if applicable.

The determination of Substantial Completion shall be made by the Owner after consultation with the Architect and shall be documented by a Certificate of Substantial Completion executed by the Parties. The Certificate shall establish the date of Substantial Completion, identify any conditions applicable to occupancy, allocate responsibility for security, maintenance, utilities, insurance, and similar matters following Substantial Completion, and include a list of remaining items to be completed or corrected.

13.2 Punch List

Upon determining that the Project has reached Substantial Completion, the Owner and the Architect may prepare a Punch List identifying incomplete or deficient Work.

The Construction Manager shall diligently complete all Punch List items within the time specified by the Owner or within such other period as the Parties may agree in writing.

Preparation of a Punch List shall not relieve the Construction Manager of the obligation to complete all Work required by the Contract Documents, whether or not specifically identified on the Punch List.

13.3 Partial Occupancy

The Owner may occupy or use any completed portion of the Project before Final Completion when such occupancy will not materially interfere with the Construction Manager's performance of the remaining Work.

Partial occupancy shall not constitute acceptance of incomplete or defective Work, shall not relieve the Construction Manager of its obligations under this Agreement, and shall not commence warranty periods except as expressly agreed in writing for the occupied portion of the Work.

13.4 Final Completion

Final Completion shall occur only after the Construction Manager has completed all Work required by the Contract Documents, corrected all known deficiencies, completed all Punch List items unless expressly waived in writing by the Owner, delivered all required closeout documentation, satisfied all contractual obligations, and received written acknowledgment from the Owner that Final Completion has been achieved.

Final Completion shall not occur solely by expiration of the Contract Time or by occupancy of the Project.

13.5 Closeout Documents

As a condition precedent to Final Completion and Final Payment, the Construction Manager shall deliver all documents required by the Contract Documents, including warranties, guarantees, operation and maintenance manuals, manufacturer's literature, as-built drawings, record documents, certificates of inspection, testing reports, commissioning documentation, training records, final lien waivers, affidavits of payment, consent of surety, spare parts required by the specifications, and all other documents reasonably necessary for the operation and maintenance of the Project.

The Owner may withhold Final Payment until all required closeout documentation has been received and approved.

13.6 Warranty

The Construction Manager warrants that all Work furnished under this Agreement shall be new unless otherwise specified, shall be of good quality, shall conform to the requirements of the Contract Documents, shall be free from defects in workmanship and materials, and shall be suitable for the purposes intended by the Contract Documents.

Unless a longer period is required by the Contract Documents or provided by the manufacturer, the Construction Manager shall warrant the Work for a period of one (1) year beginning on the date of Substantial Completion.

This warranty shall be in addition to, and not in limitation of, any other warranties or remedies available under this Agreement or applicable law.

13.7 Manufacturer Warranties

The Construction Manager shall obtain and assign to the Owner the full benefit of all manufacturers' warranties applicable to materials, equipment, and systems incorporated into the Project.

Where manufacturers require specific maintenance, inspections, registration, or startup procedures as conditions of warranty coverage, the Construction Manager shall complete or coordinate such requirements before Final Completion and shall provide documentation demonstrating compliance.

13.8 Correction of Defective Work

If any portion of the Work is found to be defective, incomplete, nonconforming, or otherwise inconsistent with the Contract Documents during the applicable warranty period, the Construction Manager shall promptly correct such Work at no additional cost to the Owner.

If the Construction Manager fails to commence corrective action within a reasonable time after receiving written notice from the Owner, the Owner may, after providing any notice required by law or this Agreement, perform or cause the corrective work to be performed and recover all resulting costs from the Construction Manager or its surety.

13.9 Latent Defects

Neither Final Completion, Final Payment, expiration of the warranty period, nor acceptance of the Project shall relieve the Construction Manager of responsibility for latent defects, fraud, defective workmanship, or other deficiencies that were not reasonably discoverable during the warranty period.

The Owner shall retain all rights and remedies available under applicable law with respect to such conditions.

13.10 Emergency Repairs

If the Owner determines that a defect creates an immediate threat to public health, safety, property, or the continued operation of the Project, and the Construction Manager cannot be contacted or fails to respond within a reasonable period under the circumstances, the Owner may undertake emergency corrective measures without prior approval.

The Construction Manager shall remain responsible for the reasonable cost of correcting defects for which it is responsible under this Agreement.

Nothing contained herein shall relieve the Owner of its obligation to provide notice when reasonably practicable under the circumstances.

13.11 Maintenance During Construction

Until Final Completion, the Construction Manager shall maintain and protect the Work from damage or deterioration and shall be responsible for ordinary maintenance necessary to preserve completed construction.

If any portion of the Work is damaged prior to Final Completion, the Construction Manager shall promptly repair or replace such Work unless the damage results solely from the negligent acts or omissions of the Owner.

13.12 Training

Before Final Completion, the Construction Manager shall provide all training required by the Contract Documents for Owner personnel responsible for operating or maintaining the completed Project.

Training shall include instruction regarding operation, maintenance, emergency procedures, warranties, recommended service intervals, and any specialized systems incorporated into the Project.

Training sessions shall be documented and copies of training materials shall be delivered to the Owner.

13.13 Spare Parts and Extra Materials

The Construction Manager shall furnish all spare parts, maintenance supplies, attic stock, keys, access devices, software licenses, passwords, specialty tools, and replacement materials required by the Contract Documents.

Such items shall be properly identified, inventoried, and delivered to the Owner before Final Completion.

13.14 No Acceptance by Payment

Neither Substantial Completion, Final Completion, occupancy, inspection, progress payments, Final Payment, nor any act of the Owner shall constitute acceptance of defective Work or relieve the Construction Manager from responsibility for complying with the requirements of the Contract Documents.

The Owner expressly reserves the right to require correction of any Work not conforming to the Contract Documents, whether discovered before or after Final Completion, to the extent permitted by law.

13.15 Survival

The obligations contained in this Article shall survive Final Completion, Final Payment, expiration or termination of this Agreement, and acceptance of the Work to the extent necessary to give effect to the warranties, guarantees, and remedies provided herein or by applicable law.

ARTICLE 14

DEFAULT, SUSPENSION, AND TERMINATION

14.1 Events of Default by the Construction Manager

The occurrence of any one or more of the following shall constitute an Event of Default by the Construction Manager:

The Construction Manager fails to prosecute the Work diligently or continuously.

The Construction Manager abandons the Project or otherwise refuses to continue performance.

The Construction Manager persistently fails to provide sufficient qualified personnel, supervision, materials, equipment, or subcontractors to perform the Work.

The Construction Manager repeatedly fails to comply with the Contract Documents or materially departs from the approved Project Schedule.

The Construction Manager fails to maintain required insurance, bonds, licenses, permits, or other qualifications necessary to perform the Work.

The Construction Manager becomes insolvent, files a petition in bankruptcy, makes an assignment for the benefit of creditors, has a receiver appointed over its assets, or otherwise becomes unable to perform its contractual obligations.

The Construction Manager knowingly submits materially false payment applications, certified payrolls, cost records, invoices, or other Project documentation.

The Construction Manager materially breaches any provision of this Agreement and fails to cure such breach within the time provided herein.

14.2 Notice of Default

If the Owner determines that an Event of Default has occurred, the Owner shall provide written Notice of Default describing the nature of the default and the actions required to cure the default.

Unless the Owner determines that an emergency exists requiring immediate action, the Construction Manager shall have seven (7) calendar days after receipt of the Notice of Default to commence corrective action and shall diligently continue such corrective action until the default has been fully cured.

If the nature of the default cannot reasonably be cured within seven (7) calendar days, the Construction Manager shall, within that period, begin corrective action and provide the Owner with a written plan and schedule demonstrating how and when the default will be cured.

14.3 Failure to Cure

If the Construction Manager fails to timely cure the default or fails to diligently pursue corrective action, the Owner may exercise any remedy available under this Agreement or applicable law.

Such remedies include, without limitation, supplementing the Construction Manager's forces, withholding payment, directing the surety to perform its obligations, terminating the Agreement for cause, completing the Work through others, recovering damages, or exercising any other contractual or statutory remedy.

The Owner's exercise of one remedy shall not preclude the simultaneous or subsequent exercise of any other remedy available at law or in equity.

14.4 Suspension of the Work

The Owner may suspend all or any portion of the Work whenever the Owner determines that suspension is necessary to protect the public interest, public safety, regulatory compliance, funding, or the integrity of the Project.

During any suspension, the Construction Manager shall protect completed Work, secure the Project site, preserve materials and equipment, and minimize unnecessary costs.

If the suspension results solely from the Construction Manager's default, the Construction Manager shall not be entitled to any increase in the Contract Sum or extension of the Contract Time.

If the suspension is not attributable to the Construction Manager and materially affects Project performance, the Parties shall negotiate an equitable adjustment in accordance with this Agreement.

14.5 Termination for Cause

If the Construction Manager commits an Event of Default and fails to timely cure such default, the Owner may terminate this Agreement for cause by written notice.

Upon termination for cause, the Owner may take possession of the Project site, assume control of materials, equipment, temporary facilities, and construction documents intended for the Project to the extent permitted by law and the Contract Documents, and complete the Work by whatever method the Owner determines to be in its best interest.

The Construction Manager shall not be entitled to further payment until the Project has been completed and the total cost of completion has been determined.

If the cost of completing the Project exceeds the unpaid balance of the Contract Sum, the Construction Manager and its surety shall be jointly and severally liable for the excess costs to the extent permitted by law.

14.6 Termination for Convenience

The Owner may terminate this Agreement, in whole or in part, whenever the Owner determines that termination is in the public interest.

Such termination shall be effective upon written notice specifying the effective date of termination.

Upon receipt of a Notice of Termination for Convenience, the Construction Manager shall immediately discontinue the affected Work, place no further purchase orders except as necessary to protect the Project, terminate applicable subcontracts where appropriate, protect completed Work, and deliver all Project records and documents requested by the Owner.

The Construction Manager shall be entitled to payment only for Work properly performed through the effective date of termination together with reasonable, unavoidable costs directly resulting from the termination, less amounts previously paid.

The Construction Manager shall not be entitled to anticipated profits on Work not performed, consequential damages, lost business opportunities, or other expectancy damages arising from a termination for convenience.

14.7 Funding Termination

Because the Owner is a governmental entity subject to the Local Government Budget and Fiscal Control Act, continuation of this Agreement is subject to the lawful appropriation and availability of funds.

If sufficient funds are not appropriated or otherwise become unavailable, the Owner may terminate this Agreement without penalty upon written notice.

The Construction Manager shall be entitled only to payment for Work properly performed prior to the effective date of termination.

14.8 Termination by the Construction Manager

The Construction Manager may terminate this Agreement only if the Owner materially breaches this Agreement and fails to cure such breach within thirty (30) calendar days after receiving written notice describing the breach.

Before terminating this Agreement, the Construction Manager shall continue performance to the extent reasonably possible and shall cooperate with the Owner in minimizing disruption to the Project.

Termination by the Construction Manager shall not be permitted for disputes concerning payment amounts that are being resolved in accordance with the dispute resolution provisions of this Agreement.

14.9 Owner's Right to Complete the Work

Following termination for cause, the Owner may complete the Project using its own forces, another contractor, the surety, or any combination thereof.

The Owner may utilize materials, equipment, temporary facilities, construction documents, schedules, submittals, shop drawings, and other Project-related information necessary to complete the Work.

The Construction Manager shall cooperate in transferring the Project to the Owner or the Owner's replacement contractor.

14.10 Preservation of Records

Upon termination, regardless of the reason, the Construction Manager shall immediately preserve all Project records.

Upon request, the Construction Manager shall deliver to the Owner all Project documents, drawings, specifications, schedules, correspondence, electronic files, Building Information Models (BIM), cost records, warranties, permits, inspection reports, and other Project information in its possession that are necessary for completion, operation, or maintenance of the Project.

14.11 No Waiver

The Owner's decision not to terminate this Agreement after the occurrence of an Event of Default shall not constitute a waiver of the default or prevent the Owner from exercising any remedy with respect to that default or any subsequent default.

Acceptance of defective Work, approval of payment applications, participation in meetings, or continued occupancy of the Project shall not waive any right arising under this Agreement unless expressly stated in a written instrument executed by the Owner.

14.12 Survival of Obligations

Termination of this Agreement shall not affect rights or obligations that by their nature survive termination, including obligations relating to warranties, indemnification, audit rights, record retention, payment of outstanding obligations, correction of defective Work, dispute resolution, and any other provision intended to survive completion or termination of the Project.

ARTICLE 15

CLAIMS AND DISPUTE RESOLUTION

15.1 Purpose

The Parties acknowledge that timely identification and resolution of disputes is essential to the successful completion of the Project. The Parties agree to cooperate in good faith to resolve disagreements at the lowest practical administrative level before resorting to formal legal proceedings.

Nothing contained in this Article shall require the Owner to compromise its statutory authority or waive any defense available under applicable law.

15.2 Definition of Claim

For purposes of this Agreement, a "Claim" means a written demand by either Party seeking an adjustment of the Contract Sum, Guaranteed Maximum Price, Contract Time, or other contractual obligation arising from this Agreement.

Routine requests for payment, Requests for Information, submittals, shop drawing reviews, field observations, and ordinary contract administration activities shall not constitute Claims unless specifically identified in writing as such.

15.3 Notice of Claim

A Party asserting a Claim shall provide written notice to the other Party within fourteen (14) calendar days after becoming aware, or reasonably should have become aware, of the event giving rise to the Claim.

The notice shall describe the factual basis of the Claim, identify the contractual provisions believed to apply, estimate the amount of any monetary adjustment requested, identify any requested adjustment to the Contract Time, and include any supporting documentation then reasonably available.

Failure to provide timely notice shall bar the Claim only to the extent the delay materially prejudices the other Party's ability to investigate the matter.

15.4 Duty to Mitigate

Each Party shall take reasonable steps to mitigate damages arising from any event that may give rise to a Claim.

The Construction Manager shall not intentionally delay corrective action or suspend performance in order to increase the amount of a potential Claim.

Likewise, the Owner shall cooperate in considering reasonable mitigation measures proposed by the Construction Manager.

15.5 Continued Performance

Pending final resolution of any Claim or dispute, the Construction Manager shall continue diligent performance of the Work unless directed otherwise by the Owner or unless continuation becomes impossible through no fault of the Construction Manager.

The Owner shall continue to process undisputed payment requests in accordance with this Agreement.

The existence of a dispute shall not justify abandonment of the Project or suspension of performance unless authorized by this Agreement or applicable law.

15.6 Initial Resolution

The Parties shall first attempt to resolve Claims through discussions between their designated Project Representatives.

If the matter is not resolved within a reasonable period, either Party may request that the dispute be elevated to senior management representatives possessing authority to negotiate a resolution.

The Parties shall exchange information reasonably necessary to evaluate the dispute and shall cooperate in good faith throughout this process.

15.7 Mediation

If a Claim cannot be resolved through direct negotiations, either Party may request non-binding mediation before filing suit.

Unless otherwise agreed, mediation shall be conducted in the county where the Project is located by a mediator mutually acceptable to the Parties.

Each Party shall bear its own attorneys' fees and expenses associated with mediation. The mediator's fees shall be shared equally unless otherwise agreed.

Participation in mediation shall not constitute an admission of liability by either Party.

15.8 Litigation

If mediation does not resolve the dispute, either Party may pursue any remedy available under applicable law.

Unless otherwise required by law, venue for any legal action arising from this Agreement shall lie exclusively in the General Court of Justice of the State of North Carolina in the county where the Project is located.

This Agreement shall not be construed as requiring binding arbitration unless the Parties expressly agree in writing after the dispute arises.

15.9 Interest

Amounts ultimately determined to be properly due under this Agreement shall bear interest only to the extent required by applicable North Carolina law.

Nothing contained herein shall create any contractual right to prejudgment interest beyond that authorized by law.

15.10 Attorneys' Fees

Each Party shall bear its own attorneys' fees, expert witness fees, consultant fees, and litigation expenses unless otherwise provided by statute or awarded by a court of competent jurisdiction.

Nothing contained herein shall be interpreted as creating a contractual right to recover attorneys' fees where such recovery would not otherwise be authorized under North Carolina law.

15.11 Audit During Dispute

The Owner's audit rights shall continue notwithstanding the existence of any Claim or dispute.

The Construction Manager shall preserve all records relating to the disputed matter until final resolution of the dispute and expiration of all applicable appeal periods.

Failure to preserve relevant records may give rise to appropriate evidentiary inferences or other remedies permitted by law.

15.12 Claims by Subcontractors

The Construction Manager shall be solely responsible for resolving disputes with its subcontractors and suppliers.

No subcontractor or supplier shall have any direct claim against the Owner arising from this Agreement except to the extent expressly authorized by applicable law.

If the Construction Manager elects to sponsor a subcontractor's claim against the Owner, the Construction Manager shall remain responsible for the accuracy, completeness, and legal sufficiency of the sponsored Claim.

15.13 Waiver of Consequential Damages

To the fullest extent permitted by law, neither Party shall be liable to the other for consequential, incidental, special, exemplary, or punitive damages arising out of this Agreement.

Consequential damages include, but are not limited to, lost profits on unrelated business, loss of business opportunities, loss of financing, loss of goodwill, or indirect economic losses.

This limitation shall not apply to damages arising from fraud, willful misconduct, criminal acts, indemnification obligations expressly assumed under this Agreement, or other matters for which limitation of liability is prohibited by law.

15.14 Finality of Executed Modifications

An executed Change Order, amendment, or other written modification shall constitute a final adjustment of the matters expressly addressed therein unless the document specifically reserves additional issues for future determination.

No Party may later assert additional compensation or additional time relating to matters expressly resolved by an executed modification except upon proof of fraud, mutual mistake, or other grounds recognized under applicable law.

15.15 Survival

The provisions of this Article shall survive Final Completion, Final Payment, expiration, or termination of this Agreement to the extent necessary to resolve pending Claims or disputes arising from the Project.

ARTICLE 16

COMPLIANCE WITH LAWS

16.1 General Compliance

The Construction Manager shall perform all Work in strict compliance with all applicable federal, state, and local laws, ordinances, regulations, rules, codes, permits, and lawful orders of governmental authorities having jurisdiction over the Project.

The Construction Manager shall obtain and maintain all licenses, permits, certifications, registrations, and approvals required for the lawful performance of the Work unless the Contract Documents expressly assign responsibility for obtaining a particular permit or approval to the Owner.

The Construction Manager shall promptly notify the Owner upon becoming aware of any actual or suspected violation of law that materially affects the Project.

16.2 Licensure

The Construction Manager represents that it is properly licensed to perform the Work required by this Agreement and shall maintain all licenses required by the State of North Carolina throughout the performance of the Project.

The Construction Manager shall ensure that all subcontractors performing Work requiring licensure are likewise properly licensed and qualified.

Failure to maintain required licensure shall constitute a material breach of this Agreement.

16.3 Building Codes and Permits

The Construction Manager shall perform the Work in accordance with the North Carolina State Building Code and all other applicable construction codes in effect on the date permits are issued unless otherwise required by law.

The Construction Manager shall comply with all permit conditions applicable to the Work and shall cooperate fully with governmental inspectors.

Nothing contained herein shall relieve the Construction Manager from responsibility for performing the Work in accordance with the Contract Documents.

16.4 Occupational Safety

The Construction Manager shall be solely responsible for compliance with all applicable occupational safety and health laws and regulations, including those administered by the North Carolina Department of Labor and the Occupational Safety and Health Administration.

The Construction Manager shall establish, implement, and enforce an effective safety program for the Project and shall require all subcontractors to comply with applicable safety requirements.

The Owner's review of safety procedures or presence at the Project site shall not relieve the Construction Manager of its sole responsibility for construction site safety.

16.5 Environmental Compliance

The Construction Manager shall comply with all environmental laws applicable to the Project, including requirements relating to erosion and sedimentation control, stormwater management, air quality, waste disposal, hazardous materials, wetlands, protected species, and pollution prevention.

The Construction Manager shall immediately notify the Owner of any environmental incident, spill, release, citation, or enforcement action affecting the Project.

16.6 Immigration Compliance

The Construction Manager represents that it complies with all applicable federal and North Carolina laws governing employment eligibility verification.

To the extent required by North Carolina law, the Construction Manager shall utilize the federal E-Verify program and shall require applicable subcontractors to do the same.

Upon request, the Construction Manager shall provide certifications or documentation reasonably demonstrating compliance with applicable employment eligibility laws.

16.7 Non-Discrimination

The Construction Manager shall not discriminate against any employee, applicant, subcontractor, supplier, or member of the public on the basis of any classification protected by applicable federal or North Carolina law in connection with the performance of this Agreement.

The Construction Manager shall require substantially similar nondiscrimination obligations in its subcontracts.

16.8 Drug-Free Workplace

The Construction Manager shall maintain a workplace free from the unlawful manufacture, distribution, possession, or use of controlled substances while performing the Work.

The Construction Manager shall take appropriate corrective action if unlawful drug activity materially affects Project performance or safety.

16.9 Public Records

The Parties acknowledge that the Owner is subject to the North Carolina Public Records Law.

Records submitted to or created for the Owner in connection with this Agreement may constitute public records subject to disclosure unless otherwise protected by applicable law.

The Construction Manager shall clearly identify any information it contends is confidential or protected from disclosure. The Owner shall determine disclosure obligations in accordance with applicable law and shall not be liable for disclosure made in good-faith compliance with legal requirements.

Nothing in this Agreement shall require the Owner to withhold records that must be disclosed under North Carolina law.

16.10 Conflicts of Interest

The Construction Manager represents that no officer, employee, or agent of the Construction Manager has knowingly offered or given any gratuity, favor, employment, loan, entertainment, or thing of value in violation of applicable law to any officer, employee, or official of the Owner in connection with this Agreement.

The Construction Manager shall promptly disclose any actual or potential conflict of interest that could reasonably affect the impartial performance of this Agreement.

16.11 Gifts and Ethics

The Construction Manager shall comply with all applicable ethics laws and policies governing public contracting.

The Construction Manager shall not knowingly provide gifts, favors, compensation, or other benefits to any public official or employee in violation of applicable law.

Nothing contained herein shall prohibit customary business meals or nominal promotional items when permitted by law and applicable municipal policy.

16.12 Iran Divestment Compliance

If applicable to this Agreement, the Construction Manager represents that it is not identified on the Final Divestment List maintained by the State Treasurer pursuant to Article 6E of Chapter 147 of the North Carolina General Statutes and that it shall remain in compliance with all statutory requirements applicable to public contracts.

If this representation becomes inaccurate during the term of this Agreement, the Construction Manager shall immediately notify the Owner.

16.13 Anti-Collusion

The Construction Manager certifies that neither it nor anyone acting on its behalf has entered into any agreement, participated in any collusive conduct, or otherwise restrained competition in connection with the procurement of this Agreement.

Any finding of collusion may constitute grounds for termination, debarment, or any other remedy available under applicable law.

16.14 Compliance Audits

The Owner may, upon reasonable notice, review or audit the Construction Manager's compliance with the provisions of this Article.

The Construction Manager shall cooperate fully with such review and shall promptly provide documentation reasonably requested by the Owner demonstrating compliance with applicable legal requirements.

16.15 Continuing Duty

Compliance with applicable law is a continuing obligation throughout the performance of this Agreement.

If any change in applicable law materially affects the performance of the Work, the Construction Manager shall promptly notify the Owner so that the Parties may determine whether a modification to the Contract Documents is appropriate.

Failure to comply with applicable law may constitute a material breach of this Agreement.

ARTICLE 17

GOVERNMENTAL PROVISIONS AND LEGAL MATTERS

17.1 Governmental Immunity

Nothing contained in this Agreement shall be construed as a waiver of the governmental immunity, sovereign immunity, public official immunity, or any other immunity, defense, limitation of liability, or protection available to the Owner, its governing board, officers, employees, or agents under the Constitution and laws of the State of North Carolina or the United States.

Execution of this Agreement shall not obligate the Owner beyond the extent permitted by law, nor shall it be interpreted as creating any cause of action or remedy not otherwise authorized by law.

17.2 No Third-Party Beneficiaries

This Agreement is entered into solely for the benefit of the Parties.

Nothing contained herein shall create any contractual relationship between the Owner and any subcontractor, supplier, consultant, employee, citizen, taxpayer, or other person not a Party to this Agreement.

No third party shall have any right to enforce or rely upon this Agreement except where such right is expressly created by applicable law.

17.3 Independent Contractor

The Construction Manager is and shall remain an independent contractor.

Nothing contained in this Agreement shall be construed as creating an employer-employee relationship, partnership, joint venture, agency relationship, fiduciary relationship, or other association between the Parties beyond the contractual relationship expressly established herein.

The Construction Manager shall have exclusive control over the means, methods, techniques, sequences, and procedures of construction except as expressly provided by the Contract Documents.

17.4 Limitation of Authority

No officer, employee, consultant, architect, engineer, inspector, project representative, or agent of the Owner shall possess authority to modify this Agreement except as expressly authorized by law and the Owner's governing policies.

The Construction Manager shall not rely upon oral statements, field directives, informal communications, or apparent authority as modifying the rights or obligations established by this Agreement.

17.5 No Personal Liability

No elected official, appointed official, officer, employee, volunteer, consultant, or agent of the Owner shall be personally liable for any obligation arising under this Agreement while acting within the course and scope of official duties.

The Construction Manager agrees that any claim arising under this Agreement shall be asserted solely against the Owner in accordance with applicable law.

17.6 Approvals Required by Law

Whenever this Agreement requires approval by the governing board, manager, purchasing official, attorney, risk manager, architect, engineer, or other representative of the Owner, such approval shall be effective only when granted in accordance with applicable law and the Owner's duly adopted policies and procedures.

Administrative approval dates maintained within the Contract Information are intended solely for recordkeeping and shall not enlarge the authority of any individual official.

The Owner's records may include the following administrative approvals:

Procurement Approval: ${purchasing_approval_date}

Legal Approval: ${legal_approval_date}

Risk Management Approval: ${risk_manager_approval_date}

Manager Approval: ${manager_approval_date}

Council Approval: ${council_approval_date}

17.7 Public Funds

The Construction Manager acknowledges that payments under this Agreement are made using public funds and that the Owner is obligated to administer this Agreement in a manner that protects the public interest.

The Construction Manager shall cooperate fully with reasonable requests intended to promote accountability, transparency, efficiency, and stewardship of public resources.

17.8 Records Retention

The Construction Manager shall retain all Project records for not less than five (5) years following Final Payment or for such longer period as required by applicable law.

Upon reasonable notice, the Owner, governmental auditors, funding agencies, or other authorized governmental representatives may inspect and copy such records.

This obligation shall survive completion or termination of this Agreement.

17.9 Ownership of Project Documents

All drawings, reports, schedules, cost information, estimates, photographs, Building Information Models (BIM), digital files, correspondence, meeting minutes, and other Project documentation prepared specifically for this Project and paid for by the Owner shall become the property of the Owner upon payment, subject to any intellectual property rights retained by the Architect or other design professionals under separate agreements.

The Construction Manager shall retain the right to maintain copies for its own business records.

17.10 Intellectual Property

The Construction Manager warrants that materials, equipment, software, systems, or methods furnished under this Agreement shall not knowingly infringe any valid patent, copyright, trademark, trade secret, or other intellectual property right.

The Construction Manager shall defend and indemnify the Owner against claims arising from such infringement to the extent caused by the Construction Manager's selection or furnishing of the infringing item.

This Section shall not apply where the alleged infringement results solely from compliance with design documents furnished by the Owner or the Owner's design professional.

17.11 Cybersecurity

If the Work includes software, network-connected equipment, Building Automation Systems, security systems, operational technology, or other digital infrastructure, the Construction Manager shall implement commercially reasonable cybersecurity practices during installation, testing, commissioning, and turnover.

Default passwords shall be changed before Final Completion.

Administrative credentials shall be transferred to the Owner at Project closeout.

The Construction Manager shall promptly notify the Owner upon becoming aware of any cybersecurity incident materially affecting the Project.

17.12 Survival

The provisions of this Article relating to governmental immunity, public records, audit rights, indemnification, ownership of records, intellectual property, cybersecurity, warranties, and other provisions intended by their nature to survive shall remain in effect after Final Completion, Final Payment, or termination of this Agreement.

ARTICLE 18

GENERAL PROVISIONS

18.1 Notices

Any notice required or permitted under this Agreement shall be in writing and shall be deemed given when personally delivered, when sent by nationally recognized overnight delivery service, when deposited in the United States Mail, postage prepaid, certified mail, return receipt requested, or when transmitted electronically if receipt is acknowledged by the receiving Party.

Notices shall be directed to the representatives identified below or to such other address as either Party may designate by written notice.

Owner

${owner_company_name}
Attn: ${owner_primary_contact_name}
${owner_address_line1}
${owner_address_line2}
${owner_city_state_zip}

Email: ${owner_primary_contact_email}

Construction Manager

${counterparty_company_name}
Attn: ${counterparty_primary_contact_name}
${counterparty_address_line1}
${counterparty_address_line2}
${counterparty_city_state_zip}

Email: ${counterparty_primary_contact_email}

18.2 Assignment

The Construction Manager shall not assign this Agreement or any substantial portion of its rights or obligations without the prior written consent of the Owner.

The Owner may assign this Agreement to any successor governmental entity or other public entity authorized by law to assume responsibility for the Project.

Any attempted assignment made in violation of this Section shall be void unless subsequently ratified in writing by the Owner.

18.3 Force Majeure

Neither Party shall be considered in default to the extent performance is prevented by events beyond that Party's reasonable control, including acts of God, war, terrorism, widespread labor disturbances not caused by the affected Party, epidemic or pandemic conditions materially affecting construction activities, or governmental actions rendering performance temporarily impossible.

The affected Party shall provide prompt written notice describing the event, its anticipated duration, and the measures being undertaken to minimize its impact.

This Section shall not automatically entitle the Construction Manager to additional compensation unless expressly authorized elsewhere in this Agreement.

18.4 Governing Law

This Agreement shall be governed by and construed in accordance with the laws of the State of North Carolina without regard to its conflict-of-laws principles.

Any legal proceeding arising from this Agreement shall be maintained in a court of competent jurisdiction located within the State of North Carolina as provided in Article 15.

18.5 Severability

If any provision of this Agreement is determined by a court of competent jurisdiction to be invalid or unenforceable, the remaining provisions shall remain in full force and effect, provided the essential purpose of the Agreement is not materially impaired.

The Parties intend that any invalid provision be construed or modified, to the extent permitted by law, so as to most nearly accomplish its original purpose.

18.6 Entire Agreement

This Agreement, together with all executed amendments, Guaranteed Maximum Price Amendments, Change Orders, exhibits, and Contract Documents incorporated by reference, constitutes the entire agreement between the Parties concerning the Project.

The Parties acknowledge that no oral statements, prior negotiations, representations, or understandings not incorporated herein shall have any force or effect.

18.7 Amendments

This Agreement may be amended only by a written instrument executed by authorized representatives of both Parties.

No field directive, email correspondence, meeting discussion, course of conduct, or oral communication shall modify the terms of this Agreement unless incorporated into a written amendment executed in accordance with applicable law.

18.8 Waiver

No waiver of any breach or default shall constitute a waiver of any subsequent breach or default.

Any waiver shall be effective only if made in writing by an authorized representative of the Party granting the waiver.

Delay or failure to enforce any contractual right shall not constitute a waiver of that right.

18.9 Interpretation

This Agreement shall be interpreted as though jointly drafted by the Parties.

No rule of construction requiring interpretation against the drafting Party shall apply.

The use of the singular includes the plural where appropriate, and references to one gender include all genders where the context requires.

The words "including," "includes," and "include" shall be deemed to be followed by the phrase "without limitation."

18.10 Headings

Article titles, headings, captions, and numbering are included solely for convenience and shall not affect interpretation of this Agreement.

18.11 Counterparts

This Agreement may be executed in one or more counterparts, each of which shall be deemed an original, but all counterparts together shall constitute one and the same instrument.

18.12 Electronic Signatures

The Parties agree that signatures transmitted electronically or executed through an electronic signature platform shall be deemed original signatures and shall have the same legal force and effect as manually executed signatures to the fullest extent permitted by applicable law.

Electronic copies of this Agreement shall be admissible in evidence to the same extent as original paper documents.

18.13 Exhibits

The following exhibits, when attached and executed or incorporated by reference, are hereby made part of this Agreement:

Exhibit A – Scope of Services or Project Description

Exhibit B – Insurance Requirements

Exhibit C – Contractor Certifications

Exhibit D – General Conditions of the Contract

Exhibit E – Technical Specifications (if applicable)

Exhibit F – Drawings (if applicable)

Exhibit G – Guaranteed Maximum Price Amendment(s)

Additional exhibits may be incorporated into this Agreement by written amendment.

For administrative purposes, the Owner may also maintain an automatically generated exhibit listing:

${exhibit_list}

EXECUTION

IN WITNESS WHEREOF, the Parties, intending to be legally bound, have caused this Agreement to be executed by their duly authorized representatives.

OWNER

${owner_company_name}

By: _______________________________________

Name: ${owner_primary_contact_name}

Title: ______________________________________

Date: _______________________

Witnessed by:_____________________			(Town Seal)

Town Clerk

This Instrument has been pre audited in the manner required by the Local Government Finance Act

_________________________

Finance Director

CONSTRUCTION MANAGER

${counterparty_company_name}

By: _______________________________________

Name: ${counterparty_signer1_name}

Title: ${counterparty_signer1_title}

Date: _______________________

APPROVALS

The following approvals shall be completed if required by applicable law, municipal policy, or the procurement process. The absence of a particular approval shall not invalidate this Agreement unless such approval is legally required.

Procurement Approval

Date: ${purchasing_approval_date}

Legal Approval

Date: ${legal_approval_date}

Risk Management Approval

Date: ${risk_manager_approval_date}

Manager Approval

Date: ${manager_approval_date}

Council Approval

Date: ${council_approval_date}

CONTRACT INFORMATION

Contract Number: ${contract_number}

Contract Name: ${name}

Contract Type: ${contract_type_name}

Department: ${department_name}

Procurement Method: ${procurement_method}

Contract Value: ${total_contract_value_dollars}

Effective Date: ${start_date}

Expiration Date: ${end_date}

Record Created: ${created_at}

Last Updated: ${updated_at}